Radnor Primary School: Professional Learning Spending Plan

April 2022 – March 2023

National Mission Enabling Objectives:

1: Developing a high quality education profession (HQEP)

2: Inspirational leaders working collaboratively to raise standards (IL)

3: Strong and inclusive schools committed to excellence, equity and well-being (SIS)

4: Robust assessment, evaluation and accountability arrangements supporting a self-improving system (RAEAA)

| No. | National Mission Link | Planned Activity | Success Criteria | Funding Source | Type of spend | Cost £ |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | HQEP IL | May/June 22 KM to attend and complete Middle Leaders Development programme - Attendance of 3 modules with a variety of leadership - Includes professional dialogues with other professionals from a variety of schools. - Complete a ‘Leadership Experience Task’ linked to whole school improvement. | - Understand what middle leadership is in the current context. - Develop knowledge of leading pedagogy, delivering effective teaching and learning. - Understanding different management strategies, structures and systems. - Have positive impact on whole school improvement. | School budget PLG | Supply costs for release | 300 |
| 2 | HQEP IL | June 22 AO to attend Primary Digital Network Meeting | - Resources shared. - Develop shared understanding of progression across Science and Technology AoLE. | School budget PLG | Supply costs for release | 200 |
| 3 | HQEP IL | July 22 AO to attend Cardiff Schools Digital Meeting | - Resources shared. - Develop shared understanding of progression across Science and Technology AoLE. | School budget PLG | Supply costs for release | 200 |
| 4 | IL RAEAA | July 22 SLT to work together on Self Evaluation and School Improvement Plan - SLT members to collaboratively evaluate 21-22 SIP. - SLT to identify key areas for improvement as part of 22-23 SIP. | - Accurate picture of school strengths and areas for development formed. - Action plans to address identified areas. - Action plans shared with all stakeholders. | School budget PLG | Supply costs for release | 800 |
| 5 | IL HQEP | Sept 22 – March 23 KM to complete the Lead Practitioner course: Physical Literacy and Pedagogical Approaches Project - KM to explore the concept of physical activity across the 3-16 continuum. Specifically focusing on physical literacy and pedagogical approaches e.g. - a multiskills approach - the teaching games for understanding approach (TGfU) - the sport education model (SEM) | - KM to attend planning and discussion meetings with CSC health and well-being team - KM to undertake background reading and research - KM to share developed resources - KM to contribute case study examples to support the production of guidance material. | CSC Funded | Supply costs for release | 0 |
| 6 | IL HQEP SIS | Sept 22 – March 23 KW to complete the Lead Practitioner course: Developing approaches to embedding Welsh History (including Black, Asian and Minority Ethnic History) within the Humanities AoLE. - KW to audit Welsh history resources in school. - KW to carry out Welsh history including BAME curriculum audit. - KW to survey Radnor families to gain an understanding of the diversity of the Radnor community. - Develop a Senedd pupil group focused on Welsh and BAME history. | - School Humanities lessons to reflect different perspectives and experiences of people of varying ethnicities. - Humanities lessons to reflect the diversity of the Radnor community. - Staff and pupils to understand that the teaching of BAME history is a statutory element of curriculum reform. | CSC Funded | Supply costs for release | 0 |
| 7 | IL HQEP SIS | Sept 22 – March 23 MS to complete the Lead Practitioner course: STEM Storytime (Maths) - MS to undertake professional learning and collaborate on the use of stories to promote engagement and develop understanding across the STEM subjects. | - MS to develop a reading list and related activities to support teaching and learning in mathematics - MS to undertake background reading and research into the use of literature to promote understanding - MS to share developed resources - MS to contribute case study examples to support the production of guidance material. | CSC Funded | Supply costs for release | 0 |
| 8 | IL HQEP SIS | Sept 22 – March 23 AO and AN to complete the Lead Practitioner course: STEM Storytime (Science & Technology) - AN and AO to undertake professional learning and collaborate on the use of stories to promote engagement and develop understanding across the STEM subjects. | - AN and AO to develop a reading list and related activities to support Science & Technology - AN and AO to undertake background reading and research into the use of literature to promote understanding - AN and AO to share developed resources - AN and AO to contribute case study examples to support the production of guidance material. | CSC Funded | Supply costs for release | 0 |
| 9 | IL HQEP SIS | Sept 22 – March 23 AO and AN to complete the Lead Practitioner course: Effective literacy development in Science & Technology - AN and AO to undertake professional learning, independent research and collaboration to develop effective approaches to enhancing the use of literacy within Science & Technology. | - AN and AO to use evidence informed actionable strategies to develop pedagogy and practice for reading across Science and Technology AoLE - AN and AO to share evidence and strategies with wider staff. | CSC Funded | Supply costs for release | 0 |
| 10 | HQEP IL | Sep-Dec 22 AN Leading Digital Learning Level 1 - AN to complete Digital Leadership Level 2 developing leadership skills and enhancing practice. - Complete modules following the Professional Learning Principles of the Digital Professional Learning Journey (DPLJ) and the Professional Standards for Teaching and Leadership. | - AN to engage with a network of digital leaders to develop and share effective practice, strategies and pedagogies - AN to lead staff in developing knowledge and understanding of digital learning and the Digital Competence Framework (DCF) responsibilities within Curriculum for Wales - AN to support staff in improving their knowledge and understanding of supporting Hwb platforms to improve teaching, learning and leading of digital skills e.g. 360 Cymru and 360 Safe | School budget PLG | Supply costs for release | 800 |
| 11 | HQEP IL | Jan- May 2023 AN Leading Digital Learning Level 2 - AN to complete Digital Leadership Level 2 developing leadership skills and enhancing practice. - Complete modules following the Professional Learning Principles of the Digital Professional Learning Journey (DPLJ) and the Professional Standards for Teaching and Leadership. | - AN to engage with a network of digital leaders to develop and share effective practice, strategies and pedagogies - AN to lead staff in developing knowledge and understanding of digital learning and the Digital Competence Framework (DCF) responsibilities within Curriculum for Wales - AN to support staff in improving their knowledge and understanding of supporting Hwb platforms to improve teaching, learning and leading of digital skills e.g. 360 Cymru and 360 Safe | School budget PLG | Supply costs for release | 600 |
| 12 | HQEP | Oct 22- Jan 23 AO Robotics – Richard Clements - AO to work with Y6 pupils on the CSC Robotics schools networking project focused on developing Science and Technology AoLE. | - Y6 pupils involved in project to improve their understanding of the Computation What Matters statement. - Pupils to share learning with younger children as part of Radnor University course modules. | School budget PLG | Supply costs for release | 400 |
| 13 | HQEP | Oct/Nov 22 KM Crucial Crew - Pupils and staff to attend seminars focused on various public services. - Support pupils in accessing work related experiences. | - Pupils to share information with wider school community. - Link Crucial Crew project work to work related experiences aspect of curriculum. | School budget PLG | Supply costs for release | 200 |
| 14 | SIS HQEP | Oct 22 ES Super Ambassadors - Pupils and staff to attend training focusing on Super Ambassadors scheme and UNCRC. - ES to share Super Ambassadors scheme with staff. | - Pupils to use Super Ambassadors scheme to support UNCRC delivery in school. - Pupils to share information with wider school during assemblies. - Staff to use Super Ambassadors scheme to embed teaching of ‘rights’. | School budget PLG | Supply costs for release | 200 |
| 15 | HQEP | Oct 22 AO to attend ICT with Mr P: Creative and Purposeful Learning ICT Conference. - AO to create bank of digital tools and platforms to share with staff - To ‘team teach’ with Y3-6 staff using strategies shared at conference. | - AO to create a bank of resources and lesson ideas and share with all staff. - Time to be allocated for AO to team teach alongside Y3-6 staff to share ICT teaching strategies (Spring 23). | School budget PLG | Supply costs for release Course costs | 422 |
| 16 | IL RAEAA | Sep 22 – Dec 22 Curriculum leads to meet with cluster school staff to work on curriculum design. - SP & MS to attend cluster meetings focusing on the Health and Wellbeing AoLE. - KM to attend cluster meeting focusing on the Health and Wellbeing AoLE. - AO to attend cluster meeting focusing on the Science and Technology AoLE. - Nominated staff member to attend cluster meeting focusing on the Expressive Arts AoLE. | - Staff members to incorporate AoLE concepts in planning. - Cluster meeting attendees to share information, documents and actions with wider staff. | Collaboration fund | Supply costs for release | 0 |
| 17 | HQEP | JG to develop use of school library. - Audit library resources. - Source library books. - Organise books based on genre and level. | - Library used to promote a love of reading. - Better engagement of pupils with library resources. | School budget PLG | Supply costs for release | 400 |
| 18 | HQEP | EO to develop use of Expressive Arts room. - Parent and family skills survey sent out asking for specialist skills and arts resources. - Expressive Arts resources sources. - EO to lead staff and pupil groups in using the room. | - Improved use of arts resources. - Expressive Arts lessons are broad and exciting covering a range of disciplines, including music, digital media and performance. | School budget PLG | Supply costs for release | 200 |
| 19 | HQEP | SP/JG/NB to develop use of ‘Mission Room’ for Y3 and 4 pupils. - Staff to research use of continuous and enhanced provision in PS2 classrooms. - Staff to design learning opportunities linked to 4 purposes. | - Staff members include elements of Y2 provision in PS2 classrooms. - Pupils independently access tasks and resources linked to themes and 4 purposes. - Y3 and 4 pupils have opportunities to access role play and practical resources. | School budget PLG | Supply costs for release | 200 |
| 20 | HQEP | JL to carry out action research into effective use of the outdoor spaces for learning. - JL to visit other schools to observe effective use of outdoor learning. - Purchase/source necessary outdoor equipment. | - Trial and evaluate different approaches to outdoor learning. - Improve look and function of reception outdoor areas. - Provide pupils with purposeful learning opportunities outdoors. | School budget PLG | Supply costs for release | 200 |
| 21 | RAEAA | Autum Term 2022 Curriculum Leads to meet and design new curriculum and approach to planning. - SP and MS to create new planning proforma and share with all staff. - SP and MS to design curriculum vision. | - Planning documents to be used by all teachers for Yma O Hyd theme (Spring 2023) - Staff to outline purposeful, rich task for pupils to demonstrate learning at the end of the theme. - SLT to monitor use of new planning documents. | School budget PLG | Supply costs for release | 800 |
| 22 | HQEP | Spring Term 2023 EO to attend training as part of the Lead Creative Schools project. - Embedding the Expressive Arts AoLE as part of the wider school curriculum. - Design and create a school mural celebrating Radnor pupils’ Active Travel initiative. | - A ‘lead creative practitioner’ working alongside pupils to create a school art piece. - A ‘lead creative practitioner’ supporting Expressive Arts AoLE team members in planning opportunities for pupils to use appropriate knowledge, skills and experiences. | Arts Council for Wales Grant | Supply costs for release | 200 |
| 23 | SIS HQEP | January 2023 Gareth Coombs staff training on Assessment for Learning - Training focused on how to capture progress of the individual learner, both in the moment of learning, and overtime for each of the four purposes - Opportunities to consider how different groups of learners make progress, and how this links to the school’s self-evaluation cycle | - Staff to understand what the expectations for assessment in the new curriculum are, and its implications for the school’s self-evaluation cycle. - Staff to understand how to embed assessment ‘as’ Learning so that assessment becomes indistinguishable from learning for each of the four purposes. - SLT to create an agreed and progressive approach to AfL and share with teaching staff. | School budget | Training cost | 250 |
|  |  |  |  |  | Total Cost | 6372 |
|  |  |  |  |  | Total Allocation | 6343 |
|  |  |  |  |  | Variance | -29 |